## Sheet1
Phase 1: Data Understanding and Initial Modelling (Week 4-6)
Indentify core tables in Van Dijk's database
Decide which columns are relevant for reporting and which to drop
Build Hubs, Sats, and Link for the relevant tables
Build standardized DV2 views
Phase 2: Expand & Stabilize DV2 Model (7-10)
Create all remaining hubs/sats/links for the core tables
Run the full load in parked and validate data consistency
Configure incremential logic
Validate end-to-end loads (raw - parked - DV2)
Do the full data flow for one Van Dijk KPI
Check automated vs. manual reports for accuracy and differences
Demo to stakeholders and adjust based on feedback
Phase 3: Data Mapping & Allignment (11-14)
Create column-level mapping (Van Dijk - Move)
Create value-level mapping
Create mapping views that apply the transformations
Test mappings to confirm business alignment
Validate combined data for correctness
Phase 4: Reporting Automation (15-16)
Identify the reports that need to be automated
Rebuild the reports in Bold BI using the mapped DV2 views
Automate refresh schedules in Bold BI
Check automated vs. manual reports for accuracy and differences
Demo to stakeholders and adjust based on feedback
Final report for the project
Phase 5: Validation and Documentation (17-20)
Perfrom end-to-end validation to check if everything is working
Document the DV2 structure, logic, mapping rules, BI setup - Data Model Architecture
Final stakeholder validation
Final report for the project
Final presentation/demo