## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Task reflection / notes
Week 1
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-09-01 | Done | Max 4 hours tasks | Meetup with the company supervisor and colleagues in the office | Meeting | A1 | 1 | 1 | 0
2025-09-01 | Done | Max 4 hours tasks | Presentation on introduction to Move Group company | Meeting | A1 | 2 | 2 | 0
2025-09-01 | Done | Max 4 hours tasks | Presentation on how the business operates | Meeting | A1 | 1 | 1 | 0
2025-09-01 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-01 | Done | Max 4 hours tasks | Presentation on how the business operates | Meeting | A1 | 2 | 2 | 0
2025-09-01 | Done | Max 4 hours tasks | Introduction to Ixolution | Workshop | A1 | 2 | 2 | 0 | Ixolution is the TMS system Move Intremodal uses for their transport management
2025-09-02 | Done | Max 4 hours tasks | Presentation on how the business operates | Meeting | A1 | 2 | 2 | 0
2025-09-02 | Done | Max 4 hours tasks | Follow the introduction course in Move Academy | Workshop | A1 | 2 | 2 | 0
2025-09-02 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-02 | Done | Max 4 hours tasks | Follow the introduction course in Move Academy | Workshop | A1 | 2 | 2 | 0 | Move Academy - platform for inside education of the Move Group members
2025-09-02 | Done | Max 4 hours tasks | Introduction to Ixolution | Workshop | A1 | 2 | 2 | 0
2025-09-03 | Done | Max 4 hours tasks | Watchin the Introduction course in Move Academy | Study | A1 | 4 | 3 | -1
2025-09-03 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-03 | Done | Max 4 hours tasks | Learning on the operations in Ixolutions and what data it contains | Workshop | A1 | 2 | 2 | 0
2025-09-04 | Done | Max 4 hours tasks | Watchin the Introduction course in Move Academy | Study | A1 | 2 | 2 | 0
2025-09-04 | Done | Max 4 hours tasks | Introduction to Transpas | Workshop | A1 | 2 | 2 | 0 | Transpas - TMS system that Van Dijk uses for its transport management
2025-09-04 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-04 | Done | Max 4 hours tasks | Introduction to Transpas and comparison to Ixolution | Workshop | A1 | 3 | 3 | 0
2025-09-05 | Done | Max 4 hours tasks | Watchin the Introduction course in Move Academy | Study | A1 | 3 | 2 | 0
2025-09-05 | Done | Max 4 hours tasks | Introduction to Transpas and comparison to Ixolution | Workshop | A1 | 1 | 1 | 0
2025-09-05 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-05 | Done | Max 4 hours tasks | Introduction to Transpas and comparison to Ixolution | Workshop | A1 | 3 | 4 | 1
|  |  |  | Total Hours |  | 41 | 40 | -1
Week 2
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning] - if any
2025-09-08 | Done | Max 4 hours tasks | Introduction to Matillion | Study | B5 | 4 | 4 | 0 | Study on Matillion basics (jobs, transformation, orchestraction)
2025-09-08 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-08 | Done | Max 4 hours tasks | Snowlfake basics | Study | B5 | 3 | 3 | 0 | Intro to schemas, SQL, queries
2025-09-08 | Done | Max 4 hours tasks | Compare example tables between Transpas and Ixolution | Workshop | B5 | 1 | 1 | 0
2025-09-09 | Done | Max 4 hours tasks | Watchin the Introduction course in Move Academy | Study | A1 | 2 | 2 | 0
2025-09-09 | Done | Max 4 hours tasks | Learn the concept of Incremential loadig in Matillion | Study | B5 | 2 | 2 | 0 | learn about the timestamps, keys, and etc.
2025-09-09 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-09 | Done | Max 4 hours tasks | Learn the concept of Incremential loadig in Matillion | Study | B5 | 2 | 2 | 0
2025-09-09 | Done | Max 4 hours tasks | Experiment with building a jobs in Matillion | Workshop | B5 | 2 | 2 | 0
2025-09-10 | Done | Max 4 hours tasks | Experiment with building a jobs in Matillion | Workshop | B5 | 2 | 2 | 0
2025-09-10 | Done | Max 4 hours tasks | Explore the business keys and logic behind sats and hubs | Study | B5 | 2 | 2 | 0
2025-09-10 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-10 | Done | Max 4 hours tasks | Explore the business keys and logic behind sats and hubs | Study | B5 | 2 | 2 | 0
2025-09-10 | Done | Max 4 hours tasks | Create one link and lsat link between two tables | Workshop | B5 | 2 | 2 | 0
2025-09-11 | Done | Max 4 hours tasks | Check the tables in Snowflake | Workshop | B5 | 2 | 2 | 0
2025-09-11 | Done | Max 4 hours tasks | Create links between tables | Workshop | B4 | 2 | 2 | 0
2025-09-11 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-11 | Done | Max 4 hours tasks | Create a complete view in matilion out of links between tables | Workshop | B4 | 4 | 4 | 0
2025-09-12 | Done | Max 4 hours tasks | Create a complete view in matilion out of links between tables | Workshop | B4 | 2 | 2 | 0
2025-09-12 | Done | Max 4 hours tasks | Check the tables in Snowflake | Workshop | B4 | 2 | 2 | 0 | Check the tables in the database in Snowflake and try to find link between some of them.
2025-09-12 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-12 | Done | Max 4 hours tasks | Finalize a view in Matillion | Workshop | B4 | 4 | 4 | 0 | The view is made out of connections made between a lot of tables.
|  |  |  | Total Hours |  | 45 | 45 | 0
Week 3
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-09-15 | Done | Max 4 hours tasks | Working on Rit view in Matillion | Workshop | B4 | 2 | 2 | 0
2025-09-15 | Done | Max 4 hours tasks | Exploring the tables in the Database | Workshop | B4 | 2 | 2 | 0
2025-09-15 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-15 | Done | Max 4 hours tasks | Exploring the tables in the Database | Workshop | B4 | 2 | 1 | -1
2025-09-15 | Done | Max 4 hours tasks | Working on Rit view in Matillion | Workshop | B4 | 1 | 1 | 0
2025-09-16 | Done | Max 4 hours tasks | Explore the KPIs of currecnt Van Dijk reports | Meeting | B4 | 2 | 2 | 0 | Meeting with the director of Van Dijk to explore the current manual reports and the KPIs
2025-09-16 | Done | Max 4 hours tasks | Excellence center IT meeting | Meeting | B9 | 1 | 1 | 0
2025-09-16 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-16 | Done | Max 4 hours tasks | Explore the KPIs of currecnt Van Dijk reports | Meeting | B4 | 2 | 2 | 0
2025-09-16 | Done | Max 4 hours tasks | Exploring the tables in the Database | Workshop | B4 | 2 | 2 | 0
2025-09-17 | Done | Max 4 hours tasks | Creating links between tables | Workshop | B5 | 4 | 3 | -1 | Check the tables in the database in Snowflake and link the relevant ones
2025-09-17 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-17 | Done | Max 4 hours tasks | Sit next to a truck planner | Workshop | B4 | 2 | 2 | 0 | I sat with a truck planner to see how the process of receiving an order to finalizing it is done and what data they use in
2025-09-17 | Done | Max 4 hours tasks | Creating links between tables | Workshop | B5 | 2 | 2 | 0
2025-09-18 | Done | Max 4 hours tasks | Exploring the tables in the Database | Workshop | B4 | 2 | 2 | 0 | Check the tables in the database in Snowflake and find a relation between them
2025-09-18 | Done | Max 4 hours tasks | Creating links between tables | Workshop | B5 | 2 | 2 | 0 | Linking some of the relevant tables using LNK and LSAT LNK links
2025-09-18 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-18 | Done | Max 4 hours tasks | Half-day with a truck driver | Workshop | B4 | 4 | 4 | 0 | went on a half-day with a truck driver to deliver/pick some orders to see the process from the other side
2025-09-19 | Done | Max 4 hours tasks | Exploring the tables in the Database | Workshop | B4 | 4 | 3 | -1 | Check the tables in the database in Snowflake and find a relation between them
2025-09-19 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-19 | Done | Max 4 hours tasks | Finalize the first complete view in Matillion | Workshop | B5 | 4 | 4 | 0 | Finalized the first view related to the Rits (Transport Actions) in Matillion
|  |  |  | Total Hours |  | 43 | 40 | -3
Week 4
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-09-22 | Done | Max 4 hours tasks | Working on Linking the tables in Matillion | Workshop | B5 | 2 | 2 | 0
2025-09-22 | Done | Max 4 hours tasks | Exploring the tables in the Snowflake | Workshop | B4 | 2 | 2 | 0
2025-09-22 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-22 | Done | Max 4 hours tasks | Make a plan for the whole duration of the placement | Planning | B9 | 2 | 2 | 0 | Made a comprehensive plan for the whole duration of the internship divided into 5 phases
2025-09-22 | Done | Max 4 hours tasks | Continue working on the tables in Matillion | Workshop | B5 | 2 | 2 | 0
2025-09-23 | Done | Max 4 hours tasks | Weekly update meeting with Tomas | Meeting | B9 | 1 | 1 | 0 | Weekly meeting with supervisor to update him what have been done during the week and if we are stick to schedule
2025-09-23 | Done | Max 4 hours tasks | Working on the tables in Matillion | Workshop | B5 | 1 | 1 | 0
2025-09-23 | Done | Max 4 hours tasks | Excellence center IT meeting | Meeting | B9 | 1 | 1 | 0
2025-09-23 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-23 | Done | Max 4 hours tasks | Working on links to Vracht table | Workshop | B5 | 4 | 3 | -1 | Vracht table is the largest in the database and contains more than 100 columns
2025-09-24 | Done | Max 4 hours tasks | Working on links to Vracht table | Workshop | B5 | 3 | 3 | 0
2025-09-24 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-24 | Done | Max 4 hours tasks | Meeting with Sven about the planning | Meeting | B9 | 1 | 1 | 0 | Went on a meeting with Sven to discuss the planning and make adjustments where needed
2025-09-24 | Done | Max 4 hours tasks | Working on links to Vracht table | Workshop | B5 | 3 | 2 | -1
2025-09-25 | Done | Max 4 hours tasks | Exploring the tables in the Snowflake related to Vracht one | Workshop | B4 | 2 | 2 | 0
2025-09-25 | Done | Max 4 hours tasks | Working on links to Vracht table | Workshop | B5 | 2 | 2 | 0
2025-09-25 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-25 | Done | Max 4 hours tasks | Meeting with Sven about the Vracht table | Meeting | B9 | 1 | 1 | 0 | Discussed the issues with Vracht table because it contained data only for a couple of months ago
2025-09-25 | Done | Max 4 hours tasks | Finalize the Vracht view | Workshop | B5 | 2 | 2 | 0 | Made small tables linking to vracht
2025-09-26 | Done | Max 4 hours tasks | Explore tables that have to be linked to Dossier table | Workshop | B4 | 2 | 2 | 0
2025-09-26 | Done | Max 4 hours tasks | Making links to the Dossier table | Workshop | B5 | 2 | 2 | 0
2025-09-26 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-26 | Done | Max 4 hours tasks | Making links to the Dossier table | Workshop | B5 | 3 | 3 | 0 | Spent the rest of the dat on the links/hubs and sats related to Dossier
|  |  |  | Total Hours |  | 41 | 39 | -2
Week 5
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-09-29 | Done | Max 4 hours tasks | Making links to the Dossier table | Workshop | B5 | 3 | 3 | 0
2025-09-29 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-29 | Done | Max 4 hours tasks | Linking tables to vracht view | Workshop | B5 | 3 | 4 | 1
2025-09-30 | Done | Max 4 hours tasks | Update meeting with Tomas and Sven | Meeting | B9 | 1 | 1 | 0
2025-09-30 | Done | Max 4 hours tasks | Adjustments on all views | Workshop | B5 | 1 | 1 | 0 | Renaming and Managing all created view with the ways disscussed during the meeting
2025-09-30 | Done | Max 4 hours tasks | IT meeting | Meeting | B9 | 1 | 1 | 0
2025-09-30 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-09-30 | Done | Max 4 hours tasks | Setting up Snowflake authentication | Debugging | B5 | 0.5 | 0.5 | 0
2025-09-30 | Done | Max 4 hours tasks | Prepare mail to Richard | Planning | B9 | 1 | 1 | 0 | Discussed and prepared a mail to Richard about the historical data of the records
2025-09-30 | Done | Max 4 hours tasks | Linking tables to vracht view | Workshop | B5 | 3 | 3 | 0 | Creating Hubs, sats, links, and lsat links for all the tables (more than 10) linking to the vracht one
2025-10-01 | Done | Max 4 hours tasks | Linking tables to vracht view | Workshop | B5 | 4 | 3 | -1 | Creating Hubs, sats, links, and lsat links for all the tables (more than 10) linking to the vracht one
2025-10-01 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-01 | Done | Max 4 hours tasks | Linking tables to vracht view | Workshop | B5 | 3 | 3 | 0 | Creating Hubs, sats, links, and lsat links for all the tables (more than 10) linking to the vracht one
2025-10-02 | Done | Max 4 hours tasks | Linking tables to vracht view | Workshop | B5 | 3 | 2.5 | -0.5 | Creating Hubs, sats, links, and lsat links for all the tables (more than 10) linking to the vracht one
2025-10-02 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-02 | Done | Max 4 hours tasks | Linking tables to vracht view | Workshop | B5 | 3 | 4 | 1 | Creating Hubs, sats, links, and lsat links for all the tables (more than 10) linking to the vracht one
2025-10-03 | Done | Max 4 hours tasks | Experimented with Vracht_Historie table | Workshop | B4 | 3 | 2 | -1 | We added a new table to the staging, and I tried to combine them
2025-10-03 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-03 | Done | Max 4 hours tasks | Linking tables to vracht view | Workshop | B5 | 3 | 3 | 0 | Creating Hubs, sats, links, and lsat links for all the tables (more than 10) linking to the vracht one
|  |  |  | Total Hours |  | 37.5 | 37 | -0.5
Week 6
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-10-06 | Done | Max 4 hours tasks | Integrating vracht_historie | Workshop | B5 | 4 | 4 | 0 | Integrating vracht_historie with vracht, so the final table to contain all of the information
2025-10-06 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-06 | Done | Max 4 hours tasks | Prepare mail to Richard | Workshop | B9 | 1 | 1 | 0
2025-10-06 | Done | Max 4 hours tasks | Linking tables to vracht view | Workshop | B5 | 3 | 3 | 0 | Creating Hubs, sats, links, and lsat links for all the tables (more than 10) linking to the vracht one
2025-10-07 | Done | Max 4 hours tasks | Update meeting with Tomas and Sven | Meeting | B9 | 1 | 1 | 0
2025-10-07 | Done | Max 4 hours tasks | IT meeting | Meeting | B9 | 1 | 1 | 0 | Meeting with the IT department
2025-10-07 | Done | Max 4 hours tasks | Data Check | Testing | B4 | 1 | 2 | 1 | Found issue in Dossier_viiew which had duplicates
2025-10-07 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-07 | Done | Max 4 hours tasks | Resolving the issue with Dossier_view | Workshop | B5 | 3 | 3 | 0
2025-10-08 | Done | Max 4 hours tasks | Linking views | Workshop | B5 | 3 | 3 | 0 | Working on linking vrachtcal_view with vracht_historie_view
2025-10-08 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-08 | Done | Max 4 hours tasks | Linking views | Workshop | B5 | 4 | 3 | -1 | Working on combining the view to create a complete one
2025-10-09 | Done | Max 4 hours tasks | Setting up the incremential logic | Workshop | B5 | 3 | 3 | 0 | Creating Hubs, sats, links, and lsat links for all the tables in staging and set thei incremential logic with LOAD_DATE and LOAD_END_DATE
2025-10-09 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-09 | Done | Max 4 hours tasks | Setting up the incremential logic | Workshop | B5 | 4 | 3 | -1 | Creating Hubs, sats, links, and lsat links for all the tables in staging and set thei incremential logic with LOAD_DATE and LOAD_END_DATE
2025-10-10 | Done | Max 4 hours tasks | Put filters for the dates on all of the views | Workshop | B5 | 2 | 2 | 0
2025-10-10 | Done | Max 4 hours tasks | Working on vracht_dossier_rit_view | Workshop | B5 | 2 | 2 | 0 | Working on combining all main views into one combined
2025-10-10 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-10 | Done | Max 4 hours tasks | Working on vracht_dossier_rit_view | Workshop | B5 | 3 | 3 | 0 | Working on combining all main views into one combined
|  |  |  | Total Hours |  | 40 | 39 | -1
Week 7
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-10-13 | Done | Max 4 hours tasks | Working on vracht_dossier_rit_view | Workshop | B5 | 2 | 2 | 0 | Working on combining all main views into one combined
2025-10-13 | Done | Max 4 hours tasks | Create the first data mart view | Workshop | B6 | 2 | 2 | 0 | Started working on the production ready views
2025-10-13 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-13 | Done | Max 4 hours tasks | Working on the data mart views | Workshop | B6 | 3 | 4 | 1
2025-10-14 | Done | Max 4 hours tasks | Update meeting with Tomas and Sven | Meeting | B9 | 1 | 1 | 0
2025-10-14 | Done | Max 4 hours tasks | IT meeting | Meeting | B9 | 1 | 1 | 0
2025-10-14 | Done | Max 4 hours tasks | Working on the data mart views | Workshop | B6 | 1 | 1 | 0 | Containers Amounts Data Mart View
2025-10-14 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-14 | Done | Max 4 hours tasks | Working on the data mart views | Workshop | B6 | 3 | 4 | 1 | Containers Amounts Data Mart View
2025-10-15 | Done | Max 4 hours tasks | Working on the data mart views | Workshop | B6 | 3 | 3 | 0 | Containers Amounts Data Mart View
2025-10-15 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-15 | Done | Max 4 hours tasks | Working on the data mart views | Workshop | B6 | 3 | 3 | 0 | Traincosts Data Mart View
2025-10-16 | Done | Max 4 hours tasks | Working on the data mart views | Workshop | B6 | 3 | 3 | 0 | Traincosts Data Mart View
2025-10-16 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-16 | Done | Max 4 hours tasks | Working on the data mart views | Workshop | B6 | 3 | 3 | 0 | Creating the Loadingmeters per container data mart view
2025-10-17 | Done | Max 4 hours tasks | Setting up the generate tables | Workshop | B6 | 3 | 3 | 0 | Setting the orchestration job for running the views and update the data in accurate order
2025-10-17 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-17 | Done | Max 4 hours tasks | Working on the data mart views | Workshop | B6 | 3 | 4 | 1 | Creating the Loadingmeters per container data mart view
|  |  |  | Total Hours |  | 36 | 39 | 3
Week 8
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-10-20 | Done | Max 4 hours tasks | Checking the results | Testing | B6 | 4 | 3 | -1 | Checking, qurying and testing the results of the already creted views
2025-10-20 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-20 | Done | Max 4 hours tasks | Resolving issues in the data mart views | Workshop | B5 | 3 | 4 | 1 | Trying to find and minimize the differences in the data
2025-10-21 | Done | Max 4 hours tasks | Update meeting with Tomas and Sven | Meeting | B9 | 1 | 1 | 0
2025-10-21 | Done | Max 4 hours tasks | IT meeting | Meeting | B9 | 1 | 1 | 0
2025-10-21 | Done | Max 4 hours tasks | Resolving issues in the data mart views | Workshop | B5 | 2 | 2 | 0 | Trying to find and minimize the differences in the data
2025-10-21 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-21 | Done | Max 4 hours tasks | Resolving issues in the data mart views | Workshop | B5 | 4 | 3 | -1 | Trying to find and minimize the differences in the data
2025-10-22 | Done | Max 4 hours tasks | Testing queries | Workshop | B5 | 3 | 3 | 0 | Testing different queries for resolve the issues with the differences in the data I got and in the report
2025-10-22 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-22 | Done | Max 4 hours tasks | Prepare for the on-site day on Thursday | Workshop | B7 | 4 | 4 | 0 | Created document with all the things I want to discuss and all the questions I want to ask
2025-10-23 | Done | Max 4 hours tasks | On-site meeting with Joost from the Office | Meeting | B9 | 3 | 3 | 0 | Discuss the data and the queries behind it
2025-10-23 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-23 | Done | Max 4 hours tasks | Testing queries | Workshop | B5 | 3 | 3 | 0 | Testing different queries for resolve the issues with the differences in the data I got and in the report
2025-10-24 | Done | Max 4 hours tasks | Testing queries | Workshop | B5 | 3 | 3 | 0 | Testing different queries for resolve the issues with the differences in the data I got and in the report
2025-10-24 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-24 | Done | Max 4 hours tasks | Checking the other views from the report | Workshop | B4 | 3 | 3 | 0
|  |  |  | Total Hours |  | 39 | 38 | -1
Week 9
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-10-27 | Done | Max 4 hours tasks | Checking the other views from the report | Workshop | B4 | 3 | 3 | 0
2025-10-27 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-27 | Done | Max 4 hours tasks | Testing and quierying the data | Workshop | B4 | 4 | 4 | 0 | Querying the data to find the relevant data
2025-10-28 | Done | Max 4 hours tasks | Update meeting with Tomas and Sven | Meeting | B9 | 1 | 1 | 0
2025-10-28 | Done | Max 4 hours tasks | IT meeting | Meeting | B9 | 1 | 1 | 0
2025-10-28 | Done | Max 4 hours tasks | Testing and quierying the data | Workshop | B5 | 3 | 2 | -1 | Trying to find and minimize the differences in the data
2025-10-28 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-28 | Done | Max 4 hours tasks | Testing and quierying the data | Workshop | B5 | 3 | 3 | 0 | Trying to find and minimize the differences in the data
2025-10-29 | Done | Max 4 hours tasks | Testing and quierying the data | Workshop | B5 | 3 | 3 | 0 | Got the data in the containers view really close to the orignial report but there are still differences
2025-10-29 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-29 | Done | Max 4 hours tasks | Querying the data | Workshop | B5 | 3 | 3 | 0 | Trying to find a way to exclude empty containers from the view
2025-10-30 | Done | Max 4 hours tasks | Introduction to Bold BI | Study | B5 | 3 | 3 | 0 | Read papers and got introduced to Bold BI
2025-10-30 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-30 | Done | Max 4 hours tasks | Meeting with Sven | Meeting | B9 | 1 | 1.5 | 0.5 | Recreating the first view in Bold Bi together with Sven
2025-10-30 | Done | Max 4 hours tasks | Experimenting with the features in Bold Bi | Workshop | B5 | 3 | 3 | 0
2025-10-31 | Done | Max 4 hours tasks | Putting all the data sources in Bold BI | Workshop | B6 | 3 | 3 | 0 | Connecting all the data sources from Snowflake to Bold BI
2025-10-31 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-10-31 | Done | Max 4 hours tasks | Working on rebuilding the Report in Bold BI | Workshop | B6 | 3 | 3 | 0
|  |  |  | Total Hours |  | 39 | 38.5 | -0.5
Week 10
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning] - if any
2025-11-03 | Done | Max 4 hours tasks | Working on rebuilding the Report in Bold BI | Workshop | B6 | 2 | 2 | 0 | Since I haven't got the sql queries from Transpas yet, I started rebuilding the report in BoldBI and later will just update
2025-11-03 | Done | Max 4 hours tasks | Creating the widget for Loadingmeters | Workshop | B6 | 2 | 2 | 0
2025-11-03 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-03 | Done | Max 4 hours tasks | Creating the widget for Tons per container | Workshop | B6 | 2 | 2 | 0
2025-11-03 | Done | Max 4 hours tasks | Creting the widget for both Subcontractors in IT and NL | Workshop | B6 | 2 | 2 | 0
2025-11-04 | Done | Max 4 hours tasks | Update meeting with Tomas and Sven | Meeting | B9 | 1 | 1 | 0 | Weekly udate meeting with Sven and Tomas to update on the work done and remaining of it
2025-11-04 | Done | Max 4 hours tasks | Exploring the BoldBI report by now | Workshop | B6 | 1 | 1 | 0
2025-11-04 | Done | Max 4 hours tasks | Excellence center IT meeting | Workshop | B9 | 1 | 1 | 0
2025-11-04 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-04 | Done | Max 4 hours tasks | Prepared a mail to Richard from Van Dijk | Workshop | B9 | 1 | 1 | 0 | Prepared comprehensive mail to Richard from Van Dijk explaining which sql queries do I need to be sent to complete the reports
2025-11-04 | Done | Max 4 hours tasks | Experiment with SQL queries for the DataMart view | Workshop | B5 | 2 | 2 | 0 | Experimented with different SQL queries in order to get the correct data in the DataMart view, but since I don’t have the queries form the system yet it’s not easy
2025-11-05 | Done | Max 4 hours tasks | Experiment with SQL queries for the DataMart view | Workshop | B5 | 2 | 2 | 0
2025-11-05 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-05 | Done | Max 4 hours tasks | Meeting with Sven | Meeting | B9 | 1 | 1.5 | 0.5 | Went on a meeting with Sven to discuss from where in the TMS system we can find the SQL queris for the extractions
2025-11-05 | Done | Max 4 hours tasks | Exploring the SQL queries in Transpas | Workshop | B5 | 3 | 3 | 0 | Searching the SQL query relevant to extracting the contrainers information
2025-11-06 | Done | Max 4 hours tasks | Exploring the SQL queries in Transpas | Workshop | B5 | 3 | 3 | 0 | Searching the SQL query relevant to extracting the contrainers information
2025-11-06 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-06 | Done | Max 4 hours tasks | Exploring the SQL queries in Transpas | Workshop | B5 | 2 | 2 | 0 | Searching the SQL query relevant to extracting the contrainers information
2025-11-06 | Done | Max 4 hours tasks | Meeting with Sven | Meeting | B9 | 2 | 2 | 0 | Discuss the sampe of the Move dataset and assign the corresponding column from Transpas
2025-11-07 | Done | Max 4 hours tasks | Meeting with Sven | Meeting | B9 | 2 | 2 | 0 | Discuss the sampe of the Move dataset and assign the corresponding column from Transpas
2025-11-07 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-07 | Done | Max 4 hours tasks | SQL course | Study | B8 | 4 | 4 | 0 | Watched a youtube video - SQL Course for Beginners
|  |  |  | Total Hours |  | 38 | 38.5 | 0.5
Week 11
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-11-10 | Done | Max 4 hours tasks | Solving issues with access | Debugging | B5 | 4 | 4 | 0 | Had issues with the VPN and connecting to Matillion the whole day
2025-11-10 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-10 | Done | Max 4 hours tasks | Solving issues with access | Debugging | B5 | 4 | 3 | -1 | Had issues with the VPN and connecting to Matillion the whole day
2025-11-11 | Done | Max 4 hours tasks | Update meeting with mentors | Meeting | B9 | 1 | 1 |  | Company Evaluation Form - Week 10
2025-11-11 | Done | Max 4 hours tasks | IT meeting | Meeting | B9 | 1 | 1
2025-11-11 | Done | Max 4 hours tasks | Finding a solution to the problem | Debugging | B5 | 1 | 1 | 0 | Discussed with Sven what could be the problem and also contacted the IT Administrators
2025-11-11 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1
2025-11-11 | Done | Max 4 hours tasks | Connecting to Matilion from IX | Debugging | B5 | 1 | 1 | 0 | Found a way to get access to Matillion through the virtual environment of Ixolution (MOVe's TMS system)
2025-11-11 | Done | Max 4 hours tasks | Working on the data mapping | Workshop | B5 | 3 | 3 | 0 | Started with the basics of mapping - column renamings
2025-11-12 | Done | Max 4 hours tasks | Working on the data mapping | Workshop | B5 | 4 | 3 | -1 | Started with the basics of mapping - column renamings
2025-11-12 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-12 | Done | Max 4 hours tasks | Working on the data mapping | Workshop | B5 | 3 | 3 | 0 | Started with the basics of mapping - column renamings
2025-11-13 | Done | Max 4 hours tasks | Working on a new data mart view | Workshop | B5 | 4 | 4 | 0 | Working on a new data mart view, to be the source for the mapping. I made it to be on a dossier (order) level
2025-11-13 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-13 | Done | Max 4 hours tasks | Working on a new data mart view | Workshop | B5 | 4 | 4 | 0 | Working on a new data mart view, to be the source for the mapping. I made it to be on a dossier (order) level
2025-11-14 | Done | Max 4 hours tasks | Working on a new data mart view | Workshop | B5 | 3 | 3 | 0 | Working on a new data mart view, to be the source for the mapping. I made it to be on a dossier (order) level
2025-11-14 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-14 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 2 | 3 | 1 | Data Mapping according to the columns that we mapped in the sample excell file from Ixolution
|  |  |  | Total Hours |  | 40 | 39 | -1
Week 12
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-11-17 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 4 | 4 | 0 | Started with calculations for the counrty codes and the zipcodes
2025-11-17 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-17 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 4 | 3 | -1 | Making calculations for extracting and making different column out of the data e.g. SH_MONTH, SH_YEAR, SH_QUARTER and etc
2025-11-18 | Done | Max 4 hours tasks | Update meeting with mentors | Meeting | B9 | 1 | 1 | 0
2025-11-18 | Done | Max 4 hours tasks | IT meeting | Meeting | B9 | 1 | 1 | 0
2025-11-18 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 2 | 3 | 1 | Making calculations for extracting and making different column out of the data e.g. SH_MONTH, SH_YEAR, SH_QUARTER and etc
2025-11-18 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-18 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 4 | 3 | -1 | Making calculations for the dates. Creating additional columns - ACT_LEAD_TIME, REQ_LEAD_TIME, ACT_ARR_TEMR_LEAD_TIME, INTERMODAL_TIME and etc
2025-11-19 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 4 | 4 | 0 | Creating new calculation columns: LOAD_SORT_START_TIME, END_TIME, UNLOAD_TIME, CLIENT_STATUS,
2025-11-19 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-19 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 4 | 4 | 0 | Creating new calculation columns: LOAD_SORT_START_TIME, END_TIME, UNLOAD_TIME, CLIENT_STATUS,
2025-11-20 | Done | Max 4 hours tasks | Meeting with Sven | Meeting | B9 | 1 | 1 | 0
2025-11-20 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 3 | 3 | 0 | Created an additional columns in the expressions of calculator 1
2025-11-20 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-20 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 3 | 2 | -1 | Working on all left columns related to calculations made out of the dates
2025-11-21 | Done | Max 4 hours tasks | Adding additional table | Workshop | B4 | 3 | 3 | 0 | Working on joining an additional table for the ref_line
2025-11-21 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-21 | Done | Max 4 hours tasks | REF_LANE table added and mapped | Workshop | B5 | 3 | 3 | 0 | I made the join between the calculator and the new table and performed the mapping of it
|  |  |  | Total Hours |  | 42 | 40 | -2
Week 13
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-11-24 | Done | Max 4 hours tasks | Working on setting the vracht_rit view | Workshop | B5 | 4 | 3 | -1 | Changed the source of the Vracht_rit view so I get only 1 record per dossier
2025-11-24 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-24 | Done | Max 4 hours tasks | Perform data checks | Testing | B6 | 3 | 3 | 0 | Checking if the link is made the right way and if the data is accurate
2025-11-25 | Done | Max 4 hours tasks | Update meeting with mentors | Meeting | B9 | 1 | 1 | 0
2025-11-25 | Done | Max 4 hours tasks | IT meeting | Meeting | B9 | 1 | 1 | 0
2025-11-25 | Done | Max 4 hours tasks | Joining vracht_view to vracht_rit based on minvracht | Workshop | B5 | 2 | 3 | 1 | Worked on creating a separate join to the vracht_rit to get the costs of a dossier
2025-11-25 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-25 | Done | Max 4 hours tasks | Joining vracht_view to vracht_rit based on minvracht | Workshop | B5 | 3 | 3 | 0 | Worked on creating a separate join to the vracht_rit to get the costs of a dossier
2025-11-26 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 4 | 3 | -1 | Created additional tables (calculations): N/S Italy, Shipment_type, Menu_type, sales_type, office_code, #shipments and etc
2025-11-26 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-26 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 3 | 3 | 0 | Working on the expression of calcukator 2 component
2025-11-27 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 4 | 4 | 0 | Creating the expressions for time_drop_off_vs_first_departure, time_last_terminal_vs_first_delivery, range_dep_term_unloading and etc
2025-11-27 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-27 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 3 | 3 | 0 | Working on the expressions for the departure and arrival addresses, scenario code and descriptions, containerno, sector_code and etc
2025-11-28 | Done | Max 4 hours tasks | Adding additional table | Workshop | B5 | 4 | 4 | 0 | Worked on adding the additional table for the REF_HUB
2025-11-28 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-11-28 | Done | Max 4 hours tasks | Data Checks | Workshop | B6 | 3 | 4 | 1 | Perform data checks to see if the mapping if the values after the mapping are the same as in the data sample
|  |  |  | Total Hours |  | 40 | 40 | 0
Week 14
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-12-01 | Done | Max 4 hours tasks | Renaming values | Workshop | B5 | 4 | 4 | 0 | Worked on renaming a lot of values in columns related to station names, addresses and etc.
2025-12-01 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-01 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 3 | 3 | 0 | Mapping the columns and values for the company_names, trade_names, city names, address names, shipment_status and shipment_seq
2025-12-02 | Done | Max 4 hours tasks | Update meeting with mentors | Meeting | B9 | 1 | 1 | 0
2025-12-02 | Done | Max 4 hours tasks | IT meeting | Meeting | B9 | 1 | 1 | 0
2025-12-02 | Done | Max 4 hours tasks | Adding link to dossier_view | Workshop | B5 | 2 | 3 | 1 | Addiiton additional link from rit_view to the dossier in the join of vracht_rit_view
2025-12-02 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-02 | Done | Max 4 hours tasks | Adding link to dossier_view | Workshop | B5 | 3 | 3 | 0 | The added link is used to get the train costs per dossier
2025-12-03 | Done | Max 4 hours tasks | Train Costs calculation | Workshop | B5 | 3 | 3 | 0 | Worked on the calculation for the traincosts, which is on a rit level and created sql query that based on the weight divides the costs to all dossiers
2025-12-03 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-03 | Done | Max 4 hours tasks | Train Costs calculation | Workshop | B5 | 3 | 3 | 0 | Worked on the calculation for the traincosts, which is on a rit level and created sql query that based on the weight divides the costs to all dossiers
2025-12-04 | Done | Max 4 hours tasks | Adding link to dossier_view | Workshop | B5 | 3 | 3 | 0 | The added link is used to get the trucking south costs per dossier
2025-12-04 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-04 | Done | Max 4 hours tasks | Tucking South Costs calculation | Workshop | B5 | 3 | 3 | 0 | Worked on the calculation for the trucking south costs, which is on a rit level and created sql query that based on the weight divides the costs to all dossiers
2025-12-05 | Done | Max 4 hours tasks | Adding link to dossier_view | Workshop | B5 | 3 | 2 | -1 | The added link is used to get the Trucking North costs per dossier
2025-12-05 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-05 | Done | Max 4 hours tasks | Tucking North Costs calculation | Workshop | B5 | 3 | 3 | 0 | Worked on the calculation for the Trucking North costs, which is on a rit level and created sql query that based on the weight divides the costs to all dossiers
|  |  |  | Total Hours |  | 37 | 37 | 0
Week 15
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-12-08 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 4 | 4 | 0
2025-12-08 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-08 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 4 | 4 | 0 | adding new columns with calculations formulas for margins and costs/revenues
2025-12-09 | Done | Max 4 hours tasks | Update meeting with mentors | Meeting | B9 | 1 | 1 | 0
2025-12-09 | Done | Max 4 hours tasks | IT meeting | Meeting | B9 | 1 | 1 | 0
2025-12-09 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-09 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 3 | 3 | 0 | Created new calculations and column for the chargable wieght calculated by the actual, ldmtrs, cubiekmeters
2025-12-10 | Done | Max 4 hours tasks | Data Mapping | Workshop | B5 | 3 | 4 | 1 | Working on all the costs related data that needs to be mapped
2025-12-10 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-10 | Done | Max 4 hours tasks | Data checks | Testing | B6 | 3 | 3 | 0 | Perform data checks to see if the costs are mapped accuratelly
2025-12-11 | Done | Max 4 hours tasks | Creating new link to dossier_view | Workshop | B5 | 3 | 2 | -1 | Working on linking a new table called documented from where I will get datum_angekmaaks as the financial_date
2025-12-11 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-11 | Done | Max 4 hours tasks | Creating new link to dossier_view | Workshop | B5 | 2 | 2 | 2 | Working on linking a new table called documented from where I will get datum_angekmaaks as the financial_date
2025-12-12 | Done | Max 4 hours tasks | Calculations based on the financial data | Workshop | B5 | 3 | 3 | 3 | Created expressions for calculations based on the financial data - costs and revenues
2025-12-12 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-12 | Done | Max 4 hours tasks | Calculations based on the financial data | Workshop | B5 | 1 | 2 | 1
2025-12-12 | Done | Max 4 hours tasks | Perform data checks | Testing | B6 | 2 | 3 | 1 | Perform data checks to find out if the calculations for the costs and revenues are made accuratelly
|  |  |  | Total Hours |  | 35 | 37 | 2
Week 16
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-12-15 | Done | Max 4 hours tasks | Data Mapping | Testing | B5 | 4 | 4 | 0 | Finalizing last touches of data mapping
2025-12-15 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-15 | Done | Max 4 hours tasks | Data Mapping | Testing | B5 | 4 | 3 | -1 | Finalizing last touches of data mapping
2025-12-16 | Done | Max 4 hours tasks | Update meeting with mentors | Meeting | B9 | 1 | 1 | 0
2025-12-16 | Done | Max 4 hours tasks | Continue working on Data Formatting | Workshop | B5 | 1 | 2 | 1
2025-12-16 | Done | Max 4 hours tasks | Meeting with the IT team | Meeting | B9 | 1 | 1.5 | 0.5 | Meeting with the IT team in the company to give updates.
2025-12-16 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-16 | Done | Max 4 hours tasks | Continue working on Data Formatting | Workshop | B5 | 3 | 3 | 0
2025-12-17 | Done | Max 4 hours tasks | Data Formatting | Workshop | B5 | 3 | 3 | 0 | Check the irrelevancies in the data and in deal with the duplicates in the Dossier view
2025-12-17 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-17 | Done | Max 4 hours tasks | Preparation for meeting with Van Dijk | Planning | B9 | 3 | 3.5 | 0.5 | Created a separate document with all the things I have to discuss with Richard from VD about the report and the data
2025-12-18 | Done | Max 4 hours tasks | Meeting with Richard from VanDijk | Meeting | B9 | 2 | 2.5 | 0.5 | Discussed the questions I had about the data and about the views in the report. Also explained to him the irrelevant results I got to get advice from where they can be
2025-12-18 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-18 | Done | Max 4 hours tasks | Continue on the Data Formatting | Workshop | B5 | 3 | 3 | 0
2025-12-19 | Done | Max 4 hours tasks | Prepare mails to Dianne from Van Dijk and Transpas support | Workshop | B9 | 2 | 2 | 0 | Prepared mails to Transpas support about the calculation I needed for the division of the prices and to Dianne about the question I had for the report
2025-12-19 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-19 | Done | Max 4 hours tasks | Spent the rest of the day resolving the issues in the mapping | Workshop | B6 | 4 | 4 | 0
|  |  |  | Total Hours |  | 36 | 37.5 | 1.5
Week 17
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-12-22 | Done | Max 4 hours tasks | Working on data mart views | Workshop | B5 | 3 | 3 | 0 | Resoling the issues with the loading meters view for the report. Change the way of the data flow, main table and etc.
2025-12-22 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-22 | Done | Max 4 hours tasks | Working on data mart views | Workshop | B5 | 2 | 3 | 1 | Change the data for the turnover view to get accurate data in the report
2025-12-23 | Done | Max 4 hours tasks | Update meeting with mentors | Meeting | B9 | 1 | 1 | 0
2025-12-23 | Done | Max 4 hours tasks | Creating views in BoldBI | Workshop | B6 | 2 | 2 | 0 | Created view for the loading meters, Transport Turnover, new Turnover data mart it Bold BI
2025-12-23 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-23 | Done | Max 4 hours tasks | Solving issues with dossier view | Workshop | B5 | 3 | 4 | 1 | Working on the issues with the duplicates and multiple records per dossier in the Dossier_view
2025-12-23 | Done | Max 4 hours tasks | Created data mart view for Turnover Transport | Workshop | B5 | 2 | 2 | 0
2025-12-24 | Done | Max 4 hours tasks | Christmas Holidays! | Break | - | 8 | 8 | 0
2025-12-25 | Done | Max 4 hours tasks | Christmas Holidays! | Break | - | 8 | 8 | 0
2025-12-26 | Done | Max 4 hours tasks | Christmas Holidays! | Break | - | 8 | 8 | 0
|  |  |  | Total Hours |  | 39 | 41 | 2
Week 18
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning] - if any
2025-12-29 | Done | Max 4 hours tasks | Checking the data mart views | Workshop | B5 | 4 | 4 | 0 | Checking from where the duplicates in the vracht_rit view are coming
2025-12-29 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-29 | Done | Max 4 hours tasks | Working on data mart views | Workshop | B5 | 3 | 3 | 0
2025-12-30 | Done | Max 4 hours tasks | Update meeting with mentors | Meeting | B9 | 1 | 1 | 0
2025-12-30 | Done | Max 4 hours tasks | Experiment with aggregating data columns for duplicates | Workshop | B5 | 2 | 3 | 1
2025-12-30 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2025-12-30 | Done | Max 4 hours tasks | Experiment with aggregating data columns for duplicates | Workshop | B5 | 2 | 2 | 0
2025-12-31 | Done | Max 4 hours tasks | New Year's Holidays! | Break | - | 8 | 8 | 0
2026-01-01 | Done | Max 4 hours tasks | New Year's Holidays! | Break | - | 8 | 8 | 0
2026-01-02 | Done | Max 4 hours tasks | New Year's Holidays! | Break | - | 8 | 8 | 0
|  |  |  | Total Hours |  | 38 | 39 | 1
Week 19
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2026-01-05 | Done | Max 4 hours tasks | Working on data mart views | Workshop | B5 | 3 | 3 | 0
2026-01-05 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2026-01-05 | Done | Max 4 hours tasks | Writing the Portfolio | Workshop | B3 | 3 | 3 | 0 | Writing the Introduction section of the Portfolio
2026-01-06 | Done | Max 4 hours tasks | Update meeting with mentors | Meeting | B9 | 1 | 1 | 0
2026-01-06 | Done | Max 4 hours tasks | Prepare mails for the colleagues from VD | Workshop | B9 | 1 | 1 | 0
2026-01-06 | Done | Max 4 hours tasks | Writing the Portfolio | Workshop | B3 | 1 | 2 | 1 | Writing the Introduction section of the Portfolio
2026-01-06 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2026-01-06 | Done | Max 4 hours tasks | Writing the Portfolio | Workshop | B1 | 3 | 3 | 0 | Writing the Project Timeline/Plan Section of the Portfolio
2026-01-07 | Done | Max 4 hours tasks | Prepare presentation for Comeback day | Workshop | B1 | 3 | 2.5 | -0.5 | Presentation
7*1/26 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2026-01-07 | Done | Max 4 hours tasks | Prepare presentation for Comeback day | Workshop | B1 | 3 | 3 | 0 | Preparing the slides for BUAS comeback day to present what is done during the placement period
2026-01-08 | Done | Max 4 hours tasks | Prepare for presenting to the Comeback day | Study | B1 | 3 | 3 | 0
2026-01-08 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2026-01-08 | Done | Max 4 hours tasks | Presenting | Meeting | B1 | 0.5 | 0.5 | 0 | Presentation
2026-01-08 | Done | Max 4 hours tasks | Listening to the presentations of the others | Meeting | B1 | 4 | 3 | -1
2026-01-09 | Done | Max 4 hours tasks | Resolving the duplicates within Dossier records | Workshop | B5 | 3 | 3 | 0 | Found a way to keep only one record per dossier
2026-01-09 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2026-01-09 | Done | Max 4 hours tasks | Final changes on Data Mapping | Workshop | B5 | 2 | 3 | 1 | Excluding irrelevnt columns from the final mapping view, reordering all left column in the same order as in IX
2026-01-09 | Done | Max 4 hours tasks | Working on data mart views | Workshop | B5 | 2 | 2 | 0 | Created 2 additional data mart views and views in the report in Bold BI
|  |  |  | Total Hours |  | 37.5 | 38 | 0.5
Week 20
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2026-01-12 | Done | Max 4 hours tasks | Writing the Portfolio | Evidencing | B1 | 4 | 4 | 0 | Writing the Project Timeline/Plan Section of the Portfolio
2026-01-12 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2026-01-12 | Done | Max 4 hours tasks | Writing the Portfolio | Evidencing | B1 | 3 | 3 | 0 | Writing the Company description section of the Portfolio
2026-01-12 | Done | Max 4 hours tasks | Fill in the work and learning log for the last weeks | Evidencing | B7 | 1 | 1 | 0
2026-01-13 | Done | Max 4 hours tasks | Update meeting with mentors | Meeting | B9 | 0.5 | 0.5 | 0 | Company Evaluation Form Week 20
2026-01-13 | Done | Max 4 hours tasks | Meeting with the reporting team from VD | Meeting | B9 | 1.5 | 1.5 | 0 | Meeting with Dianne and Daphne from VD to validate the report
2026-01-13 | Done | Max 4 hours tasks | Working on creating data mart views | Workshop | B6 | 3 | 2.5 | -0.5 | Created an additional data mart views in Matillion for the Loadingmeters, Containers, Outsourced Costs and Tons in Belgium
2026-01-13 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2026-01-13 | Done | Max 4 hours tasks | Working on creating data mart views | Workshop | B6 | 2 | 2 | 0 | Created an additional data mart views in Matillion for the Loadingmeters, Containers, Outsourced Costs and Tons in Belgium
2026-01-13 | Done | Max 4 hours tasks | Writing the Portfolio | Evidencing | B5 | 2 | 2 | 0 | Writing the Methodology section of the portfolio
2026-01-14 | Done | Max 4 hours tasks | Writing the Portfolio | Evidencing | B5 | 3 | 3 | 0 | Writing the Methodology section of the portfolio
2026-01-14 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2026-01-14 | Done | Max 4 hours tasks | Putting the data marts in Bold Bi | Workshop | B6 | 4 | 3 | -1 | Working on creating the data sources for the new views in Bold BI and putting them in the reports
2026-01-15 | Done | Max 4 hours tasks | Writing the Portfolio | Evidencing | B6 | 3 | 3 | 0 | Writing the Evaluation and Testing Section in the Portfolio
2026-01-15 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2026-01-15 | Done | Max 4 hours tasks | Putting the data marts in Bold Bi | Workshop | B6 | 3 | 3 | 0 | Working on creating the data sources for the new views in Bold BI and putting them in the reports
2026-01-16 | Done | Max 4 hours tasks | Report checks | Testing | B6 | 3 | 3 | 0 | Checking all the views in the reports and identify issues
2026-01-16 | Done | Max 4 hours tasks | Meeting with Sven and Tomas | Meeting | B9 | 0.5 | 0.5 | 0 | Had a meeting with the mentors to validate the final results and conclude the internship
2026-01-16 | Done | Max 4 hours tasks | Lunch break | Break | - | 1 | 1 | 0
2026-01-16 | Done | Max 4 hours tasks | Perform data checks with Sven | Meeting | B6 | 1 | 1 | 0 | Checked all the data with Sven
2026-01-16 | Done | Max 4 hours tasks | Setting up the generate tables and all schedulers | Workshop | B6 | 1 | 1 | 0 | Setting up the generate tables and all schedulers to update the views on a daily basis automatically, and validate the results with Sven
2026-01-16 | Done | Max 4 hours tasks | Writing the Portfolio | Workshop | B3 | 2 | 3 | 1 | Writing the Theoretical Background and Literature Study of the Portfolio
2026-01-16 | Done | Max 4 hours tasks | Writing the Portfolio | Evidencing | B2 | 2 | 2.5 | 0.5 | Writing the Discussion and Conclusion sections of the Portfolio
|  |  |  | Total Hours |  | 44.5 | 44.5 | 0
|  |  |  | Total hours this block |  | 788.5 | 787 | -1.5

## Overview
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
A1 | W1: 0 | 0
A2 | [8 empty] | 0
A3 | [8 empty] | 0
B4 | [8 empty] | 0
B5 | [8 empty] | 0
B6 | [8 empty] | 0
C7 | [8 empty] | 0
C8 | [8 empty] | 0
TOTAL HOURS PER WEEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Use this to plan a high level allocation for all 320 hours you are expected to devote to the course during this block. How do you want to allocate your hours for each week? Why 320 hours? The European Higher Education Framework states that an academic credit is expected to require 25-28 hours to earn. You earn 15 credits per block, so you should be expected to devote 375 hours to accomplish that. CMGT students do fewer hours because the program is more intense.
Use a formula like this to get your data from Worklog sheet : =IFERROR(SUM(FILTER('Worklog_Tasks&Times'!$H$5:$H$14,'Worklog_Tasks&Times'!$F$5:$F$14=$B4)),0)

## Drop-downs
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | A1
Unplanned | Meeting | A2
Blocked | Programming | A3
In-Progress | Research | B4
Done | Testing | B5
Delayed | Workshop | B6
Cancelled | Planning | C7
| Evidencing | C8
| Debugging | C9
Lecture
Study
Unplanned
Distraction
Break